Plan to execute the market stratergy

Week 0: Preparation

Goal: Build the foundation.

- Finalize the tagline:

"Skills that get you internships and jobs — not just certificates."

Or

"From learning to landing opportunities."

- Create a tracking sheet:

- Student Name

- College

- Source (LinkedIn / Referral / Event)

- Sign-up Status

- Referral Count

- Select 1 pilot college for testing.

Week 1: Build Awareness

Goal: Make students aware of AIInsight.

- Post 3 LinkedIn posts:

- AI industry insight

- Student success story

- Career/internship tip

- Share posts in:

- WhatsApp groups

- College communities

- Instagram stories

Week 2: Campus Champion Program

Goal: Increase reach through students.

- Recruit 3–5 student ambassadors.

- Give each ambassador:

- Referral code

- Promotion message

- Registration link

- Referral rewards:

- 1 referral → Digital badge

- 3 referrals → Workshop access

- 5 referrals → Free session

Week 3: Free Event

Goal: Generate leads and registrations.

- Conduct a free Resume Building Workshops.

- Collect:

- Name

- Email

- College

- Interest Area

- Follow up within 48 hours with:

- Course details

- Registration link

Week 4: Analyze Results

Goal: Identify what works best.

Track:

- LinkedIn sign-ups

- Referral sign-ups

- Event sign-ups

Check for :

- Which channel got the most students?

- Which channel cost the least?

- Which students converted into learners?

Ongoing Improvement

- Continue LinkedIn posting.

- Run one free event every month.

- Improve beginner courses by adding:

- Mini projects

- Career roadmap

- Internship guidance

- Progress checkpoints